## About
C2 Shared action tracker
Quillmarrow Supplies Pte. Ltd. (fictional)
Fictional organisation, illustrative only, not a client case study.
Version 1.0
Date 12 February 2027 (illustrative)
Prepared by Alex Lew, reviewer and sign-off
15 shared actions (DA-01 to DA-15), status at 31 January 2027.
Owned by the DPO and reviewed at each monthly check-in. An action is Closed only when the closure evidence is filed. Revised dates need COO agreement.
I personally review and sign off every deliverable.
You appoint your own DPO. I support them.
This is practical compliance support, not legal advice. For legal advice, use a Singapore-qualified lawyer.
What's not included:
- Acting as, being named as or replacing your DPO.
- Legal advice, legal representation or submitting regulatory notifications on your behalf.
- Certification or a guarantee of compliance.
- An emergency hotline or a substitute for your own incident-response arrangements.
- Forensic investigation, penetration testing, security engineering or administering your systems.
- Holding your customer database or making changes to live systems.
- Rebuilding the whole PDPA programme, a new AI governance review or a major new project (these need a separate scope and quote).
- Healthcare-sector work or on-site delivery.
Questions about this sample: DM @alewyl1 on X, or ask for a free intro call (coffee chat).

## Actions
Fictional organisation, illustrative only, not a client case study. Quillmarrow Supplies Pte. Ltd. (fictional) is invented.
Version 1.0 · 12 February 2027 (illustrative) · Prepared by Alex Lew, reviewer and sign-off
ID | Source | Action | Owner role | Raised | Due | Revised due | Status | Closed on | Evidence (filed or needed) | Decision needed | Update at 31 Jan 2027
DA-01 | G-01 | Publish the DPO business contact and complaints route. | DPO | 2 Nov 2026 | 30 Nov 2026 | None | Closed | 27 Nov 2026 | Filed: website contact published 12 Nov 2026; B5 policy approved by the MD 20 Nov 2026; complaints process documented 27 Nov 2026. | None | Closed on target on 27 Nov 2026. The DPO contact was published on 12 Nov and the complaints process documented on 27 Nov.
DA-02 | G-02 | Put in place a consent-record method for new showroom sign-ups. | Head of Marketing | 2 Nov 2026 | 13 Nov 2026 | 4 Dec 2026 (COO) | Closed | 2 Dec 2026 | Filed: showroom sign-up form with a consent record field, in use from 2 Dec 2026; DPO check of the first entries. | None (the follow-on decision on older sign-ups is DA-03) | The consent-record method went live on 2 Dec 2026: late against the original 13 Nov target, within the 4 Dec date. Older sign-ups without a consent record are a separate decision, tracked in DA-03.
DA-03 | G-02 | Decide how to dispose of about 600 older showroom sign-up cards that have no consent record. | MD with DPO | 16 Dec 2026 | 26 Feb 2027 | None | Open |  | Needed: MD decision after lawyer advice and a dated deletion record if deletion is selected. | MD, with DPO, to decide whether to delete the cards or send a single re-permission message after lawyer advice. | The MD directed on 16 Dec 2026 that the cards be suppressed from all marketing. The delete-or-re-permission decision remains open pending lawyer advice.
DA-04 | G-04 | Publish the job-application and showroom sign-up notices and install CCTV signage. | DPO | 2 Nov 2026 | 13 Nov 2026 | 11 Dec 2026 (COO) | Closed | 9 Dec 2026 | Filed: job-application notice dated 20 Nov 2026, showroom sign-up notice dated 2 Dec 2026 and CCTV signage installed 9 Dec 2026. | None | All listed notices and signage were in place by 9 Dec 2026, before the revised target of 11 Dec.
DA-05 | G-05 / AR-06 | Close AR-06 and agree that DV-01 forwards requests within one working day. | DPO | 2 Nov 2026 | 30 Nov 2026 | None | Closed | 25 Nov 2026 | Filed: DV-01 written agreement dated 25 Nov 2026 to forward requests within one working day; AR-06 recorded as closed 18 Nov 2026. | None | AR-06 was closed on 18 Nov 2026, late, mainly because DV-01 took 9 days to forward it. DV-01 agreed in writing on 25 Nov to forward requests within one working day.
DA-06 | G-07 / DV-02 | Enable MFA for Fictional ShopCloud administrator accounts. | IT Manager | 2 Nov 2026 | 13 Nov 2026 | None | Closed | 19 Nov 2026 | Filed: ShopCloud admin settings record dated 19 Nov 2026 showing MFA required for administrator accounts. | None | MFA was enabled on 19 Nov 2026, six days after the original target.
DA-07 | G-07 / DV-03 | Complete a review of Fictional Harbour IT administrator access. | IT Manager | 2 Nov 2026 | 13 Nov 2026 | 31 Jan 2027 (COO) | Closed | 22 Jan 2027 | Filed: administrator access review completed 22 Jan 2027; two dormant administrator accounts removed. | None | The revised target was 31 Jan 2027. The review was completed on 22 Jan and two dormant administrator accounts were removed.
DA-08 | G-08 / RS-02 / RS-12 / RS-13 | Confirm the retention decisions for RS-02, RS-12 and RS-13 after accountant and lawyer advice. | MD with DPO and Finance Director | 2 Nov 2026 | 31 Jan 2027 | None | Overdue |  | Needed: MD decision recorded for RS-02, RS-12 and RS-13 and B8 v1.2 issued. | MD to confirm the retention positions for RS-02, RS-12 and RS-13; decision is on the 12 Feb 2027 agenda. | Accountant and lawyer advice was received on 20 Jan 2027. The MD decision was not made by the 31 Jan due date and is on the 12 Feb agenda.
DA-09 | G-08 / RS-04 / RS-10 | Dispose of declined credit applications and complete the visitor-log clean-up. | Finance Director and Warehouse Manager | 18 Dec 2026 | 28 Feb 2027 | None | In progress |  | Filed so far: RS-04 disposal record dated 25 Jan 2027. Needed: disposal record for the RS-10 visitor-log clean-up. | None | RS-04 declined credit applications were disposed of on 25 Jan 2027 with a disposal record. The RS-10 visitor-log clean-up remains due by 28 Feb 2027.
DA-10 | G-09 / DV-01 | Obtain DV-01's signed data protection addendum. | COO | 2 Nov 2026 | 15 Dec 2026 | 31 Jan 2027 (COO) | Overdue |  | Needed: signed DV-01 data protection addendum and updated B10 transfer record. | If the addendum is still unsigned on 28 Feb 2027: continue under interim minimisation with a further deadline, or cut the Malaysia fulfilment data to a minimum and look at alternatives. For the MD on 12 Feb 2027. | The addendum was sent to DV-01 on 6 Jan 2027 and remained unsigned on 31 Jan, missing the revised date. Interim minimisation has applied since 7 Dec 2026: customer email addresses are no longer sent to DV-01.
DA-11 | G-09 / DV-02 | Obtain and record evidence of Fictional ShopCloud's hosting and backup regions. | IT Manager | 2 Nov 2026 | 15 Dec 2026 | None | Closed | 14 Dec 2026 | Filed: Fictional ShopCloud written confirmation dated 14 Dec 2026 that primary hosting is in Singapore and encrypted backups are in Japan; B10 transfer note updated. | None | Written hosting and backup-region evidence was received on 14 Dec 2026 and the B10 transfer note was updated.
DA-12 | INC-2026-11 | Turn on an external-recipient warning and a short delayed send for the Finance team's mail. | IT Manager | 10 Dec 2026 | 15 Jan 2027 | None | Closed | 13 Jan 2027 | Filed: IT Manager's change record dated 13 Jan 2027 and a test email showing the warning. | None | Closed on 13 Jan 2027, ahead of the 15 Jan due date. The action arose from INC-2026-11, a statement of account emailed to the wrong B2B customer on 10 Dec 2026.
DA-13 | C4 / DV-04 | Complete the conditions required before the DV-04 pilot starts. | Head of Customer Service | 18 Jan 2027 | 28 Feb 2027 | None | Open |  | Needed: missing vendor evidence received; lawyer's contract points agreed; AI reply suggestions off; access limited to ticket and order-lookup roles; B9 and B3 updated. | DPO to confirm all conditions are met before the pilot; COO approval dated 20 Jan 2027 is subject to DA-13. | The DPO's decision on 18 Jan was to proceed to a three-month pilot from 1 Mar 2027 only if the conditions are met. The COO approved subject to those conditions on 20 Jan; DA-13 remains open and on track.
DA-14 | C7 drill | Update B11 to add the ShopCloud incident contact, COO as deputy decision-maker and a calendar-day reminder. | DPO | 21 Jan 2027 | 15 Feb 2027 | None | Open |  | Needed: B11 v1.1 approved by the MD, with the ShopCloud incident contact, the COO as deputy decision-maker and a calendar-day reminder on the form. | MD to approve B11 v1.1 (on the 12 Feb 2027 agenda) | The 21 Jan 2027 tabletop drill found that participants first counted working days, nobody had ShopCloud's incident contact and B11 named no deputy decision-maker. The DPO has drafted B11 v1.1 for MD approval on 12 Feb 2027.
DA-15 | C6 refresher | Complete the refresher catch-up for staff who missed the 26 Jan session. | HR Manager | 26 Jan 2027 | 26 Feb 2027 | None | Open |  | Needed: attendance or completion record for the recorded session and completed five-question check for the eight staff who missed the 26 Jan session. | None | Eight staff were absent from the 26 Jan 2027 refresher, mostly warehouse night shift and leave. They are to complete the recorded session and five-question check by 26 Feb 2027.