## About
C5 Policy and procedure change log
Quillmarrow Supplies Pte. Ltd. (fictional)
Fictional organisation, illustrative only, not a client case study.
Version 1.0
Date 12 February 2027 (illustrative)
Prepared by Alex Lew, reviewer and sign-off
10 changes (PC-01 to PC-10), November 2026 to January 2027.
No change is live until its approver has approved it. Superseded versions are kept under B8.
I personally review and sign off every deliverable.
You appoint your own DPO. I support them.
This is practical compliance support, not legal advice. For legal advice, use a Singapore-qualified lawyer.
What's not included:
- Acting as, being named as or replacing your DPO.
- Legal advice, legal representation or submitting regulatory notifications on your behalf.
- Certification or a guarantee of compliance.
- An emergency hotline or a substitute for your own incident-response arrangements.
- Forensic investigation, penetration testing, security engineering or administering your systems.
- Holding your customer database or making changes to live systems.
- Rebuilding the whole PDPA programme, a new AI governance review or a major new project (these need a separate scope and quote).
- Healthcare-sector work or on-site delivery.
Questions about this sample: DM @alewyl1 on X, or ask for a free intro call (coffee chat).

## Changes
Fictional organisation, illustrative only, not a client case study. Quillmarrow Supplies Pte. Ltd. (fictional) is invented.
Version 1.0 · 12 February 2027 (illustrative) · Prepared by Alex Lew, reviewer and sign-off
ID | Date | Document | Version | Change | Reason | Approver | Staff communication | Next review
PC-01 | 13 Nov 2026 | B11 Breach management plan | v1.0 | The breach management plan from the handover pack was adopted and issued to the incident team. | Addressed G-10 by establishing the incident record and separate decision log. | MD | Teams post to relevant staff, 13 Nov 2026 | After the January 2027 drill; v1.1 in progress under DA-14
PC-02 | 13 Nov 2026 | B4 Website privacy notice | v1.1 | The updated website privacy notice was published. | Addressed G-04 and the notice actions recorded in B2. | DPO | Teams post to relevant staff, 13 Nov 2026 | November 2027
PC-03 | 20 Nov 2026 | B5 Data protection policy | v1.0 | The data protection policy was approved. | Addressed G-01 by documenting the programme policy. | MD | Team briefing, 20 Nov 2026 | November 2027
PC-04 | 20 Nov 2026 | B12 Do Not Call procedure | v1.0 | The DNC procedure was approved. | Addressed G-11 and established the process for the planned telemarketing campaign. | Head of Marketing | Team briefing, 20 Nov 2026 | November 2027
PC-05 | 27 Nov 2026 | B5 Data protection policy, annex A | v1.0 to v1.1 | The complaints process was added as annex A. | Addressed the complaints-process action under G-01. | DPO | Teams post to relevant staff, 27 Nov 2026 | November 2027
PC-06 | 9 Dec 2026 | B4 Job-application, showroom sign-up and CCTV notices | v1.1 | B4 v1.1 brings together the job-application notice (in use from 20 Nov 2026) and the showroom sign-up notice (from 2 Dec 2026), and adds the CCTV signage installed on 9 Dec 2026. | Closed G-04 on 9 Dec 2026, within the revised date of 11 Dec 2026 agreed by the COO. | DPO | Team briefing, 9 Dec 2026 | December 2027
PC-07 | 10 Dec 2026 | B5 Data protection policy, annex B | v1.1 to v1.2 | The CCTV purpose and access statement was added as annex B; use for staff matters requires prior review by the DPO and HR Manager. | Addressed G-03 and set a review route for use of CCTV in staff matters. | MD | Teams post to relevant staff, 10 Dec 2026 | December 2027
PC-08 | 18 Dec 2026 | B8 Retention schedule | v1.1 | The MD approved the retention schedule except for RS-02, RS-12 and RS-13, which remain awaiting confirmation. | Addressed G-08; the three outstanding retention decisions are tracked in DA-08. | MD | Teams post to relevant staff, 18 Dec 2026 | When the MD decides RS-02, RS-12 and RS-13 (DA-08)
PC-09 | 13 Jan 2027 | B7 Access and correction procedure | v1.0 to v1.1 | The procedure was updated to require partner request forwarding within one working day and shared mailboxes to forward request-like emails to the DPO. | Followed the AR-06 forwarding delay (DA-05) and the AR-13 late acknowledgement. | DPO | Teams post to relevant staff, 13 Jan 2027 | January 2028
PC-10 | 20 Jan 2027 | B9 Vendor and data-intermediary checklist | v1.0 to v1.1 | The DV-04 record and its pilot conditions were added. | Recorded the vendor review and conditional pilot decision for DV-04; conditions are tracked in DA-13. | COO | Team briefing, 20 Jan 2027 | Before the DV-04 pilot starts (DA-13)