## About
B2 Gap review and action plan
Quillmarrow Supplies Pte. Ltd. (fictional)
Fictional organisation, illustrative only, not a client case study.
Version 1.0
Date 30 October 2026 (illustrative)
Prepared by Alex Lew, reviewer and sign-off
11 review areas (G-01 to G-11) with RAG, owner roles, evidence to close and target dates.
RAG reflects the evidence seen during the review, not a legal conclusion.
I personally review and sign off every deliverable.
You appoint your own DPO. I support them.
This is practical compliance support, not legal advice. For legal advice, use a Singapore-qualified lawyer.
What's not included:
- Acting as your DPO. You appoint your own DPO; I prepare the handover and can support them separately.
- Legal advice, legal contract drafting, representation or a guarantee of compliance.
- Forensic investigation, penetration testing, security engineering or implementing changes in live systems.
- A detailed AI governance review or ISO/IEC 42001 readiness check unless separately scoped.
- Ongoing document upkeep after handover, unless agreed through monthly DPO support.
- Healthcare-sector work or on-site delivery.
Questions about this sample: DM @alewyl1 on X, or ask for a free intro call (coffee chat).

## Gap tracker
Fictional organisation, illustrative only, not a client case study. Quillmarrow Supplies Pte. Ltd. (fictional) is invented.
Version 1.0 · 30 October 2026 (illustrative) · Prepared by Alex Lew, reviewer and sign-off
ID | Area | RAG | Current state | Gap | Priority | Action | Owner role | Evidence to close | Target date | Status
G-01 | Accountability | Amber | The Head of Operations has been appointed as DPO. The review found that the DPO contact has not yet been published and no written data protection policy was supplied. | The policy, published contact, complaints process and staff communication are not evidenced. | P2 within 60 days | Adopt the data protection policy, publish the DPO contact and document the complaints process; update B2. | Head of Operations | MD-approved policy, website capture showing dpo@quillmarrow.example, and documented complaints process. | 30 Nov 2026 | Open
G-02 | Consent | Amber | The web-shop checkout consent for orders was reported as satisfactory. The B2B account form has a pre-ticked marketing consent box, and no consent records were supplied for showroom sign-ups. | The B2B marketing choice needs correction and Quillmarrow needs evidence of showroom sign-up choices and records. | P1 now | Remove the pre-ticked marketing box, establish an affirmative consent record for showroom sign-ups and update B2. | Head of Marketing | Updated B2B form, showroom sign-up process and sample consent records showing the person's choice and its source. | 13 Nov 2026 | Open
G-03 | Purpose limitation | Amber | The review found that recorded purposes were broadly reasonable. The supplied case facts also state that CCTV was used once in a staff timekeeping dispute, outside its stated purpose. | The CCTV purpose, access and escalation process do not show how out-of-purpose use will be prevented or reviewed. | P2 within 60 days | Document permitted CCTV purposes and access, prohibit unrelated use unless reviewed and authorised, and record the change in B2. | Showroom Supervisor | Approved CCTV purpose and access procedure, staff communication record and documented approval route for exceptional use. | 15 Dec 2026 | Open
G-04 | Notification | Red | The website has a generic privacy statement dated 2019. No privacy notice was supplied for the job application form, showroom sign-up or CCTV signage. | People are not provided with current, channel-specific information at these collection points. | P1 now | Replace the website statement and prepare notices for job applicants, showroom sign-ups and CCTV; record the work in B2. | Head of Operations | Approved notices and dated screenshots or copies showing publication at each specified collection point. | 13 Nov 2026 | Open
G-05 | Access and correction | Amber | Customer Service handles requests ad hoc and no request log was supplied. One request took 41 days; six sample request scenarios, AR-01 to AR-06, identify web-shop, employee, B2B, CCTV and partner-forwarded requests. | There is no consistent intake, tracking, escalation or response evidence against the organisation's stated target. | P1 now | Adopt the access and correction procedure, log the AR-01 to AR-06 scenarios and train receiving teams; update B2. | Head of Customer Service | Approved procedure, request log template, completed scenario walkthroughs and staff briefing record. | 13 Nov 2026 | Open
G-06 | Accuracy | Green | B2B account details are verified at onboarding. Sales conducts an annual check, as reported in the supplied review facts. | The review did not receive records demonstrating the annual checks or how corrections are carried through relevant systems. | P3 within 90 days | Retain evidence of the Sales verification cycle and document how corrections are reflected in relevant records; update B2. | Sales Manager | Dated verification record and documented correction procedure or sample completed correction record. | 29 Jan 2027 | Open
G-07 | Protection | Amber | A SharePoint folder containing customer records was link-shared to anyone with the link for two days, as described in the breach scenario. Microsoft 365 has MFA, but Fictional ShopCloud admin does not; Fictional Harbour IT admin access has not been reviewed. | The link-sharing event highlights exposure risk, while ShopCloud admin MFA and review of MSP privileged access remain open. | P1 now | Review external-link settings and privileged access, enable MFA for ShopCloud admin where available, and record remediation in B2 and B11. | IT Manager | Dated access review, ShopCloud admin MFA configuration evidence, SharePoint sharing-control evidence and remediation record linked to B11. | 13 Nov 2026 | Open
G-08 | Retention limitation | Red | No retention schedule was supplied and the case facts state that records are kept indefinitely. CCTV is reported by Quillmarrow to be overwritten at about 30 days. | Retention and disposal decisions are missing for the record types in RS-01 to RS-20; accounting and tax periods need confirmation with an accountant or lawyer. | P1 now | Complete and approve B8, assigning a justified retention decision and disposal method for each RS record type, with accounting and tax periods flagged for confirmation. | Head of Operations | Approved B8 schedule covering RS-01 to RS-20, with owners, disposal methods and documented accountant or lawyer confirmation where relevant. | 15 Dec 2026 | Open
G-09 | Transfer limitation | Amber | DV-01 receives Malaysia delivery data under a contract with a confidentiality clause but no data protection clauses. Fictional ShopCloud's hosting region is to be confirmed. | Transfer safeguards and the platform's hosting location are not evidenced; the contract and processing arrangements need review. | P2 within 60 days | Confirm Fictional ShopCloud's hosting region and review DV-01 terms and transfer safeguards, documenting the outcome and any agreed measures in B2. | Head of Operations | Written ShopCloud hosting-region confirmation and documented DV-01 contract review with agreed transfer safeguards or recorded unresolved issues. | 15 Dec 2026 | Open
G-10 | Data breach notification | Red | No breach plan, assessment form or decision log was supplied. INC-2026-07 was handled by email; the case facts separately record its assessment and the MD and DPO's notification decision. | Quillmarrow lacks a documented C.A.R.E. response route and consistent records separating assessment facts from the notification decision. | P1 now | Adopt B11, including the assessment form, separate decision log, escalation route and roles for intermediary reports; test it using INC-2026-07. | Head of Operations | MD-approved B11, completed tabletop exercise record using INC-2026-07 and logged corrective actions. | 13 Nov 2026 | Open
G-11 | Do Not Call (DNC) provisions | Amber | A telemarketing campaign to SME owners is planned. No DNC register-check process was supplied, and sender details are not standardised. | The campaign lacks a documented check, suppression and sender-identification process before contact. | P1 now | Document the campaign DNC check and suppression process, standardise sender details and record the check in B2 before calls begin. | Head of Marketing | Approved campaign procedure, standard sender script and a sample check record showing the check was made within the validity period set by the PDPC (confirm the current period). | 13 Nov 2026 | Open